## Features
Features backlog
ID | Capability | Backlog Item (Feature or Story) | Comments | Phase | Tshirt Sizing | Story Points | Business Uncertainty | Technical Complexity | BEST CASE | MOST LIKELY | WORST CASE | CONE of Uncertainty | Tshirt Size for Cone Calc
1 | Pantalla Cliente | formulario de registro | formulario de registro de cliente | Next | S | 5 | Low | Medium | 4.75 | 5 | 5.25 | 5% | S
2 | Pantalla Cliente | Login | SSO SQL | Next | M | 8 | Low | High | 6.4 | 8 | 9.6 | 20% | M
3 | Pantalla Cliente | Agendamiento citas | formulario de agendamiento | Next | M | 8 | Low | Low | 8 | 8 | 8 | 0% | M
4 | Capability 1 | sistema de calificacion | use modelo de estrellas para lavador | Next | S | 3 | Low | Medium | 2.85 | 3 | 3.15 | 5% | S
5 | Capability 1 | Feature 5 |  | Next | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
6 | Capability 1 | Feature 6 |  | Next | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
7 | Capability 1 | Feature 7 |  | Last | zero |  | Medium | Medium | 0 | 0 | 0 | 0% | zero
8 | Capability 1 | Feature 8 |  | Next | zero |  | Medium | Low | 0 | 0 | 0 | 0% | zero
9 | Capability 1 | Feature 9 |  | Next | zero |  | Low | Medium | 0 | 0 | 0 | 0% | zero
10 | Capability 1 | Feature 10 |  | Next | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
11 | Capability 1 | Feature 11 |  | Later | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
12 | Capability 1 | Feature 12 |  | Later | zero |  | High | Medium | 0 | 0 | 0 | 0% | zero
13 | Capability 1 | Feature 13 |  | Next | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
14 | Capability 2 | Feature 14 |  | Next | zero |  | Low | Medium | 0 | 0 | 0 | 0% | zero
15 | Capability 2 | Feature 15 |  | Later | zero |  | Medium | Low | 0 | 0 | 0 | 0% | zero
16 | Capability 2 | Feature 16 |  | Later | zero |  | Medium | Medium | 0 | 0 | 0 | 0% | zero
17 | Capability 2 | Feature 17 |  | Later | zero |  | Medium | Low | 0 | 0 | 0 | 0% | zero
18 | Capability 2 | Feature 18 |  | Later | zero |  | Low | Medium | 0 | 0 | 0 | 0% | zero
19 | Capability 2 | Feature 19 |  | Last | zero |  | Low | Medium | 0 | 0 | 0 | 0% | zero
20 | Capability 2 | Feature 20 |  | Later | zero |  | Medium | Low | 0 | 0 | 0 | 0% | zero
21 | Capability 2 | Feature 21 |  | Last | zero |  | Medium | Medium | 0 | 0 | 0 | 0% | zero
22 | Capability 2 | Feature 22 |  | Last | zero |  | High | Low | 0 | 0 | 0 | 0% | zero
23 | Capability 2 | Feature 23 |  | Last | zero |  | Low | Low | 0 | 0 | 0 | 0% | zero
Total | [8 empty] | 22 | 24 | 26

## Features Analysis
Phase: | Next
Features analysis by Size | [5 empty] | Features analysis by Uncertainty |  |  |  |  | Features analysis by Complexity
Row Labels | %tage | Number of Uss | Best Case (SP) | Most Likely (SP) | Worst Case (SP) | Row Labels | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP) | Row Labels | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
XS | 0% | 0 | 0 | 0 | 0 | Low | 100% | 22 | 24 | 26 | Low | 33.33% | 8 | 8 | 8
S | 33.33% | 2 | 7.6 | 8 | 8.4 | Medium | 0% | 0 | 0 | 0 | Medium | 33.33% | 7.6 | 8 | 8.4
M | 66.67% | 2 | 14.4 | 16 | 17.6 | High | 0% | 0 | 0 | 0 | High | 33.33% | 6.4 | 8 | 9.6
L | 0% | 0 | 0 | 0 | 0 | Total | 100% | 22 | 24 | 26 | Total | 100% | 22 | 24 | 26
XL | 0% | 0 | 0 | 0 | 0
XXL | 0% | 0 | 0 | 0 | 0
Total | 100% | 4 | 22 | 24 | 26

## Cone of Uncertainty
| Project timeline | No of Sprints in Build Phase | Total no of Sprint including (setup, UAT ..) | Y
| Best Case | 0 | 0 | 0
|  | 4 | 6 | 10
| Most Likely | 0 | 0 | 0
|  | 4 | 6 | 10
| Worst Case | 0 | 0 | 0
|  | 4 | 6 | 10
| Threshold | 0 | 0 | 10
|  | 22 | 22 | 10
Build | Average Velocity(SP) per Sprint | 20
Operate | Number of sprints for Operate (handover, releases, UAT, SIT, application support, etc.) | 0
Technical Items | 1. Environment setup for teams (install tools, access to cloud services etc.) 2. Create all environments needed by the engagement: dev, system test, pre-prod, production. 3. Create a delivery pipeline. 4. NFRs 5. Security testing | 2
Visual Parameters
| Cone Size | 0
| Threshold | 10
| Length of threshold | 20
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add Avg Velocity for the Team(s) that will implement the features
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If needed please add here any effort for the UAT / Preparation for Go-Live. If more granularity is needed then “whole” sprints, please mark this as zero and add in the ‘Features Analysis’ sheet a line with the needed effort
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add if needed. If this is part of the Discovery - you will not needed

## byUncertainty (hidden)
Phase | (All)
Business Uncertainty / Size | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
Low | 19.58% | 75.65 | 101.5 | 127.35
Medium | 27.19% | 83.8 | 141 | 198.2
High | 53.23% | 69.7 | 276 | 482.3
Total | 100% | 229.15 | 518.5 | 807.85

## byComplexity (hidden)
Phase | (All)
Technical Complexity / Size | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
Low | 42.91% | 117.3 | 222.5 | 327.7
Medium | 49.37% | 103.85 | 256 | 408.15
High | 7.715% | 8 | 40 | 72
Total | 100% | 229.15 | 518.5 | 807.85

## Assumtions
# | Assumptions
1
2
3
4
5
6
7
8
9
10
11
12

## Definition of Done
This template uses an average velocity (Story Points) to calculate the cone of uncertainty (duration interval). For that to be valid you'll need the estimation team to allign on what "done" means and what activities are included. The below is an example as a starting points and should be tailored case-by-case
Development
Technical Implementation Plan confirmed with architects/TL [if needed].
Code written and tested locally.
Unit Tests developed for Back-end ( 80% code coverage) and Front-end ( 60% code coverage).
Code reviewed and approved by at least one mandatory approval.
Documentation of model/controllers/sequence diagrams [if needed].
IDs for FE elements ( where needed). - checked on code review & testing.
Configuration check - (if needed ) added in release notes.
Release notes updated.
Sonar execution on review - no critical issues accepted.
English labels available in CMS ( if needed).
All defects reported by testing fixed.
Deployment/Demo
Changes deployed successfully to Openshift Director env (no build error + sonar passed successfully ) >= 5 SP (2 days before sprint ends), only bug fixing will be allowed.
Deployment freeze also 3 hours before demo.
Testing
Test cases written in Zephyr.
Application tested against the mock layer, including error cases and edge.
Manual functional test 100% test coverage on test environment.
Manual test (basic and advanced) cases executed and passing.
Exploratory testing executed.
Testing passed 100% on Test Environment.
All issues reported as bugs and linked to the stories.
Acceptance criteria fulfilled.
Test data is documented.
NFR fulfilled.
Quality Acceptance.
No issues with severity worse than Major.
Feature documented in TBD owner.
User story is updated with latest information/requirements.
Automated testing
Automated tests written.
Automated tests committed to Git.
Automated tests executed and validated.
Other considerations
(TBD story by story
OR add a separate story)
*all to be covered with Acceptance criteria.
Performance.
Security.
Error handling.
Localization.
In-house usability testing.

## Team Shape
Delivery Team(s) Shape
Name of Person (if known) | Role | Grade
| Scrum Master | CL
| Senior Developer | SC
| Developer | SE
| Developer | SE
| Senior Tester | CL
| Tester | EN
| Architect | SC
| Project Manager | CL
| Business Analyst | CL

## ConeOfUncertainty Setup
Value | Business Uncertainty Low | Business Uncertainty Medium | Business Uncertainty High | Sizing GoldieLocks: Tshirt to SP Average Lookup |  | Business Uncertainty Values | Phases
zero | 0% | 0% | 0% | zero | 0 | Low | Next
XS | 0% | 5% | 10% | XS | 1.5 | Medium | Later
S | 0% | 10% | 20% | S | 4 | High | Last
M | 0% | 20% | 25% | M | 10.5 |  | (All)
L | 20% | 25% | 30% | L | 20
XL | 25% | 30% | 40% | XL | 40
XXL | 30% | 40% | 50% | XXL | 100
Value | Technical Complexity Low | Technical Complexity Medium | Technical Complexity High | Sizing GoldieLocks: Tshirt to SP Average Lookup |  | Technical Complexity Values
zero | 0% | 0% | 0% | 0 | zero | Low
XS | 0% | 0% | 5% | 1 | XS | Medium
S | 0% | 5% | 10% | 2 | XS | High
M | 0% | 10% | 20% | 3 | S
L | 10% | 15% | 30% | 5 | S
XL | 15% | 20% | 40% | 8 | M
XXL | 20% | 40% | 50% | 13 | M
|  |  |  | 20 | L
|  |  |  | 40 | XL
|  |  |  | 100 | XXL
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The cone of uncertainty based on statistical data for a product You could adjust these value with your statistics if needed
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: M size correspont to 8 or 13 SP the average is 10.5
Note on P2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Possible values for Business Uncertainty
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase when we plan to implement the feature
Note on P11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Possible values for Technical Complexity